## Bug Report for User, address, E
Bug# | Bug title | Description | Priority | Severity | Steps to reproduce | Expected result | actual result | Status | Assigned to | QA Remarks | Dev Remarks
BRFUDM01 |  |  | High | Medium | 1) Go to : https://amaderit.net/demo/hr/login 2) Click Log in 3) Click to the Logo | 1) After click logo, page will redirect AmaderHR Home page. 2) "Remember me" option should save the id and password | 1) Logo button is not working 2) Remember option is not working | New
BRFUDM02 |  |  | Medium | Low | 1) go to : https://amaderit.net/demo/hr/ 2) Click Address Management from left sidebar. 3) Click "Division" | 1) Pagination with small data. | 1) Pagination is not shown. Large data in on a single page. | New
BRFUDM03 |  |  | Medium | Low | 1) go to : https://amaderit.net/demo/hr/ 2) Click Address Management from left sidebar. 3) Click "Division" 4) Click Add Division 4) Click Add Division | 1) After delete a division add the same division again | 1) It shows already exist. | New
BRFUDM04 |  |  | Medium | Low | 1) go to : https://amaderit.net/demo/hr/ 2) Click Address Management from left sidebar. 3) Click "Division" 3) Click "Import" | 1) It will import a .csv file in database | 1) Failed to import csv file | New
BRFUDM05 |  |  | High | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click Address Management from left sidebar. 3) Click "District" | 1) Pagination for less row & Search will show. | 1) Pagination is very large. | New
BRFUDM06 |  |  | Medium | Low | 1) go to : https://amaderit.net/demo/hr/ 2) Click Address Management from left sidebar. 3) Click "District" | 1) Access id district page. | 1) After modifying Division District page is not working. | New
BRFUDM07 |  |  | Medium | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click Address Management from left sidebar. 3) Click "District" | 1) Click Export, will export a .csv file | 1) Not exporting any csv file. | New
BRFUDM08 |  |  | High | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click Education Management from left sidebar. 3) Click "Degree" | 1) Pagination with small data & Search will show. | 1) Pagination is not shown. Large data in on a single page. | New
BRFUDM09 |  |  | High | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click Education Management from left sidebar. 3) Click "Degree" | 1) Click Export, will export a .pdf file 2) Click Import, will import a .csv file in database. | 1) Failed to export any file. 2) No option for import file. | New
BRFUDM10 |  |  | Medium | Low | 1) go to : https://amaderit.net/demo/hr/ 2) Click Education Management from left sidebar. 3) Click "Institute Name" | 1) Pagination for less row & Search will show. | 1) Pagination is not shown. Large data in on a single page. | New
BRTMSI011 |  |  | High | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click Education Management from left sidebar. 3) Click "Institute Name" 4) Click Export. | 1) It will export a .pdf file | 1) Failed to export any file. | New

## Bug Report for Bank Management
Bug# | Bug title | Description | Priority | Severity | Steps to reproduce | Expected result | Actual result | Status | Assigned to | QA Remarks | Dev Remarks
BRFBM01 |  |  | Medium | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click Bank Management from left sidebar. 3) Click "Bank Name" | 1) Pagination with small data & Search will show. | 1) Pagination is not shown. Large data in on a single page. | New
BRFBM02 |  |  | High | High | 1) 1) go to : https://amaderit.net/demo/hr/ 2) Click Bank Management from left sidebar. 3) Click "Branch Name" | 1) Pagination for less row & Search will show. | 1) Pagination is not shown. Large data in on a single page. | New
BRFBM03 |  |  | Medium | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click Bank Management from left sidebar. 3) Click "Branch name" 4) Click "Add Branch" | 1) Character limit show 2) Save with existing bank name show error | 1) There is no character limit. 3) Save with existing bank name is also taken. | New
BRFBM04 |  |  | Medium | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click Bank Management from left sidebar. 3) Click "Bank Name" 4) Click Edit bank icon | 1) Character limit show. | 1) There is no character limit. | New
BRFBM05 |  |  | Medium | Medium | 1) go to : https://amaderit.net/demo/hr/ 2) Click bank Management from left sidebar. 3) Click "Bank Name" 4) Click Export. | 1) It will export a .pdf file | 1) Failed to export any file | New